## Hoja1
Month \ Week | 1 | 2 | 3 | 4
1 | continue literature review & get an overview of the data |  | set up a script for working with the data | Information about Valparaíso
2 | find suitable GMPE and apply it to the catalogue |  | build up the exposure model of the water network
3 | check tsunami inundation maps | cumulative effect of seismic and tsunami hazard |  | fragility functions
4 | simulate pipe damages and estimate losses |  | Calculate uncertainty in the losses | time buffer
5 | Build a map with GIS | identify representative scenarios
6 | Writing the thesis